## Bill Page
| Project |  | Briggate
| Main Contractor |  | HG Construction
| Main Contractor QS |  | Harvey Craven
| Quba QS |  | Adam Davis
| VO Number |  | VO006
| Revision |  | 1
| Date |  | 2024-07-29
VO006 - ADD & OMIT Abseiling Cladding Works; as per marked-up drawings provided | QTY | Unit | Rate | Total
Costs to carry out cladding works via abseiling on the various locations as discussed; as per the marked-up drawings provided
Add Abseiling
GRC Sub-Frame Installation, inclusive of brackets, insulation and fire stops | 295 | m2 | 148.625 | 43844.375
GRC Installation | 295 | m2 | 334.4062 | 98649.8438
K-Roc Installation | 112 | m2 | 190.24 | 21306.88
75mm K-Roc Installation, including additional sub-frame | 74 | m2 | 359.6725 | 26615.765
Vieo Zinc Cladding Installation | 186 | m2 | 190.24 | 35384.64
Sub-Total of Add £225,801.50
Omit
GRC Sub-Frame Installation, inclusive of brackets, insulation and fire stops | 295 | m2 | -64.6519 | -19072.3031
GRC Installation | 295 | m2 | -104.0375 | -30691.0625
K-Roc Installation | 186 | m2 | -51.7215 | -9620.199
Vieo Cladding Installation | 186 | m2 | -77.5823 | -14430.2985
Sub-Total of Omit £73,813.86
Design |  | NA
Abseiling equipment; inclusive of ropes, rope protectors, strops, harnesses, lanyards. Anchor points and specialist lifting equipment by the MC | 1 | item | 5535 | 5535
|  |  | Total | 157522.6406
Reason for VO
It is not possible for HG to provide scaffold access for the areas as discussed and highlighted on the marked-up drawings. We have therefore provided this add and omit to carry out the installation of these areas via abseiling
Exclusions
Vertical lifting of materials and skips assumed to be provided by others.
Abseiling equipment and ropes to be provided by HG
This VO is based upon a dedicated spider crane being provided by HG for us to carry out the works.

## Price Sheet
CALCULATIONS
[7 empty] | LABOUR |  | MATERIAL |  |  |  | FIXINGS |  | MARKUP |  | MCD |  | CHARGEABLE RATES
[13 empty] | 0% |  | 45% |  | 2.5%
ITEM REFERENCE | DESCRIPTION | QTY | UNIT | Rate | Total | Notes | Unit | Total | Supplier | Quote Reference | Unit | Total | Unit | £ p | Unit | Total | Unit | Total | Unit | Total | CONTROL
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Costs to carry out cladding works via abseiling on the various locations as discussed; as per the marked-up drawings proivded |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Add |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| GRC Sub-Frame Installation, inclusive of brackets and insualtion | 295 | m2 | 148.625 | 43844.375 |  | 100 | 29500 |  |  |  | 0 | 0 | 0 | 45 | 13275 | 3.625 | 1069.375 | 148.625 | 43844.375 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| GRC Installation | 295 | m2 | 334.4062 | 98649.8438 |  | 225 | 66375 |  |  |  | 0 | 0 | 0 | 101.25 | 29868.75 | 8.1562 | 2406.0938 | 334.4062 | 98649.8438 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| K-Roc Installation | 112 | m2 | 190.24 | 21306.88 |  | 128 | 14336 |  |  |  | 0 | 0 | 0 | 57.6 | 6451.2 | 4.64 | 519.68 | 190.24 | 21306.88 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| 75mm K-Roc Installation | 74 | m2 | 359.6725 | 26615.765 |  | 242 | 17908 |  |  |  | 0 | 0 | 0 | 108.9 | 8058.6 | 8.7725 | 649.165 | 359.6725 | 26615.765 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Vieo Zinc Cladding Installation | 186 | m2 | 190.24 | 35384.64 |  | 128 | 23808 |  |  |  | 0 | 0 | 0 | 57.6 | 10713.6 | 4.64 | 863.04 | 190.24 | 35384.64 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Omit |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| GRC Sub-Frame Installation, inclusive of brackets and insualtion | 295 | m2 | -64.6519 | -19072.3031 |  | -43.5 | -12832.5 |  |  |  | 0 | 0 | 0 | -19.575 | -5774.625 | -1.5769 | -465.1781 | -64.6519 | -19072.3031 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| GRC Installation | 295 | m2 | -104.0375 | -30691.0625 |  | -70 | -20650 |  |  |  | 0 | 0 | 0 | -31.5 | -9292.5 | -2.5375 | -748.5625 | -104.0375 | -30691.0625 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| K-Roc Installation | 186 | m2 | -51.7215 | -9620.199 |  | -34.8 | -6472.8 |  |  |  | 0 | 0 | 0 | -15.66 | -2912.76 | -1.2615 | -234.639 | -51.7215 | -9620.199 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Vieo Zinc Cladding Installation | 186 | m2 | -77.5823 | -14430.2985 |  | -52.2 | -9709.2 |  |  |  | 0 | 0 | 0 | -23.49 | -4369.14 | -1.8922 | -351.9585 | -77.5823 | -14430.2985 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
| Abseiling equipment; inclusive of ropes, harnesses, lanyards. Anchor points and specialist lifting equipment by others. | 1 | item | 5535 | 5535 |  |  | 0 |  |  | 4500 | 4500 | 0 | 0 | 900 | 900 | 135 | 135 | 5535 | 5535 | TRUE
|  |  |  | 0 | 0 |  |  | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
|  |  |  | Sub Total | 157522.6406 |  |  | 102262.5 |  |  |  | 4500 |  | 0 |  | 46918.125 |  |  |  | -6278.4581 | FALSE

## Take-Off
Timesing | Dimension | Squaring | Unit | Description
|  | 249 | m2 | K -Roc 25mm
|  | 121 | m2 | K-Roc 75mm
|  | 186 | m2 | Vieo Zinc
|  | 291 | m2 | GRC