## Project Details
Project Name: Brixton Rise
Project Address: Kennington Park, London SW9, UK, UK
Contractor: Eldridge Urban Build
Contractor QS: ClearEdge Consulting
Contract Value: £68256.42
Assigned QS User: Daniel Toreas
Assigned PM User: Daniel Toreas
Created By: Daniel Toreas
Start Date: 2025-04-17
End Date: 2025-07-17
Project Description: A single-storey rear extension to an outbuilding at a university featuring a high-performance EPDM flat roofing system. The project involves thermal insulation upgrades, timber fascia detailing.
Created At: 2025-06-26

## V01
| Project: | Brixton Rise
| Main Contractor: | Eldridge Urban Build
| Main Contractor QS: | ClearEdge Consulting
| Sub Contractor QS: | Philip Wasko
| VO Number: | V01
| Revision: | Revision 2
SI Ref:
| Date: | 2025-08-14 | Total
|  | Total | 0
Reason for VO:
[Reason for vo type here]
Exclusions:

## V02
| Project: |  | Brixton Rise
| Main Contractor: |  | Eldridge Urban Build
| Main Contractor QS: |  | ClearEdge Consulting
| Sub Contractor QS: |  | Philip Wasko
| VO Number: |  | V02
| Revision: |  | Revision 1
SI Ref:
| Date: |  | 2025-08-14 | Total
Addition of Rooflight
Form opening in roof, preparation works, installation of rooflight and weather around. | 1 | item | 6988 | 6988
Mobile Crane | 1 | item | included | included
|  |  | Total | 6988
Reason for VO:
New roofight has been introduced to the scheme.
Exclusions:

## V03
| Project: |  | Brixton Rise
| Main Contractor: |  | Eldridge Urban Build
| Main Contractor QS: |  | ClearEdge Consulting
| Sub Contractor QS: |  | Philip Wasko
| VO Number: |  | V03
| Revision: |  | Revision 1
SI Ref:
| Date: |  | 2025-08-14 | Total
Change in Fascia Material
Remove Existing Installed uPVC fascia and dispose from site | 1 | item | 1468 | 1468
Installation of Red Cedar Fascia instea | 99 | lm | 88 | 8712
|  |  | Total | 10180
Reason for VO:
Substitution of standard uPVC fascias with pre-treated Western Red Cedar boards, including stainless steel fixings and protective finish.
Exclusions:

## V04
| Project: |  | Brixton Rise
| Main Contractor: |  | Eldridge Urban Build
| Main Contractor QS: |  | ClearEdge Consulting
| Sub Contractor QS: |  | Philip Wasko
| VO Number: |  | V04
| Revision: |  | Rev2 (C)
SI Ref:
| Date: |  | 2025-08-14 | Total
Addtional Wall
Preparation Works | 1 | item | 1500 | 1500
Materials | 1 | item | 2000 | 2000
Installation | 50 | m2 | 80 | 4000
Commercial Discount |  |  |  | -500
|  |  | Total | 7000
Reason for VO:
The architect came to site and decided they wanted a new wall built
Exclusions:

## V06
| Project: |  | Brixton Rise
| Main Contractor: |  | Eldridge Urban Build
| Main Contractor QS: |  | ClearEdge Consulting
| Sub Contractor QS: |  | Philip Wasko
| VO Number: |  | V06
| Revision: |  | Revision 1
SI Ref:
| Date: |  | 2025-08-26
Additional Flooring Works | QTY | Unit | Rate (£) | Total
Additional Flooring Works | 52 | m2 | 66 | 3432
|  |  | Total | 3432
Reason for VO:
Additional Flooring Works
Exclusions:

## V07
| Project: |  | Brixton Rise
| Main Contractor: |  | Eldridge Urban Build
| Main Contractor QS: |  | ClearEdge Consulting
| Sub Contractor QS: |  | Daniel Toreas
| VO Number: |  | V07
| Revision: |  | Revision 1
| SI Ref: |  | 1
| Date: |  | 2025-11-26
Additional Joinery Required | QTY | Unit | Rate (£) | Total
Additional desk at nurse station | 1 | item | 3500 | 3500
|  |  | Total | 3500
Reason for VO:
Additional Desk at nurse base station
Exclusions:

## V08
| Project: |  | Brixton Rise
| Main Contractor: |  | Eldridge Urban Build
| Main Contractor QS: |  | ClearEdge Consulting
| Sub Contractor QS: |  | Daniel Toreas
| VO Number: |  | V08
| Revision: |  | Revision 2
| SI Ref: |  | TBC
| Date: |  | 2025-11-26
Addiitonal Desk at Nurse Call | QTY | Unit | Rate (£) | Total
Additional Nurse Call Station | 1 | item | 2689 | 2689
MCD |  |  |  | -268.9
|  |  | Total | 2420.1
Reason for VO:
Following site instruction after weekly meeting.
Exclusions: